## begroting
Internal budget |  |  |  | Role | Project leader | Team member (code reviews)
Gridgeom in C++ - phase 3 |  |  |  | Name | Carniato, L. | Julian Hofer
|  |  |  | Tariff | D | A
|  |  |  | SO-tariff | 135 | 107
Planning | Activity | Product | Hours | Cost
Part 1 | Implement curvilinear grid from splines (orthogonal, interactive) | unit tests + grid editor | 68 | 9068 | 64 | 4 | make interactive, solve last bugs
Part 1 | Implement curvilinear grid transfinite (transfinite) | unit tests + grid editor | 44 | 5828 | 40 | 4
Part 2 | Implement merge nodes | unit tests + grid editor | 28 | 3668 | 24 | 4
Part 2 | Implement “curvilinear to unstructured grid converter” | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 3 | Add third party triangulation library (triangle.c) | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 3 | Implement triangular mesh in polygon | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 3 | Implement polygon edges refinement | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 3 | Mesh boundary to polygon | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 4 | Implement “Make Rectangular grid” | unit tests + grid editor | 28 | 3668 | 24 | 4
Part 4 | Implement “Make Rectangular grid within polygon” | unit tests + grid editor | 28 | 3668 | 24 | 4
Part 4 | Implement “Make Rectangular from samples” | unit tests + grid editor | 28 | 3668 | 24 | 4 | this should be easy
Part 4 | Implement “Make grid from samples” | unit tests + grid editor | 28 | 3668 | 24 | 4
Part 5 | Grid refinement from samples | unit tests + grid editor | 68 | 9068 | 64 | 4
Part 5 | Edge/nodes manipulations: move nodes, delete edges | unit tests + grid editor | 20 | 2588 | 16 | 4
Part 5 | Offset of a polygon perimeter | unit tests + grid editor | 20 | 2588 | 16 | 4
|  | Total (hours) | 460 |  | 400 | 60
|  | Total (€) |  | 60420 | 54000 | 6420
week number | hours spent
2 | 36
3 | 36
4 | 20
5 | 31
6 | 20
7 | 26
8 | 20
9 | 22
10 | 14
13 | 30
14 | 33
15 | 34
16
budget
Total hours spent so far | 322 | 43470

## Sheet1
ctrl + x | interactor instructions
shift + c | polygong offset
use buffers for nodes and edges
generate curvilinear grid from spline: spli api, create cpp file
dx | 5
dtmax | 1.5964