## begroting
Internal budget |  |  |  | Role | Project leader | Team member (code reviews)
Gridgeom in C++ (phase 4) |  |  |  | Name | Carniato, L.
|  |  |  | Tariff | D
|  |  |  | SO-tariff | 135
Planning | Activity | Product | Hours | Cost
Part 1: leftovers from previous plan | Implement curvilinear grid transfinite (transfinite) | unit tests + grid editor hookup (button) | 40 | 5400 | 40
Part 1: leftovers from previous plan | translate fliplinks to C++ with unit test | unit tests + grid editor hookup (button) | 32 | 4320 | 32
Part 2: missing functions for the river group | translate pol2curvi to C++ with unit tests | unit tests + grid editor hookup (button) | 24 | 3240 | 24
Part 2: missing functions for the river group | translate pol2curvi_tri to C++ with unit tests | unit tests + grid editor hookup (button) | 16 | 2160 | 16
Convert cartesian to spherical
|  | Total (hours) | 112 |  | 112 | 0
|  | Total (€) |  | 15120 | 15120 | 0

## rgfgrid buttons
Buttons |  |  | Is included in Grid Editor (NA = not available, A = available)?
File
Import
|  | Grid (Delft3D-FLOW) | A
|  | UGRID (D-Flow FM) | NA
|  | Grid (ADCIRC) | NA
|  | Grid (ROMS) | NA
|  | Grid (Telemac) | NA
|  | Grid (UnTRIM) | NA
Edit
Regular grid
|  | Line freeze | NA (line operations on structured grid)
|  | Line Shift | NA (line operations on structured grid)
|  | Line Attraction | NA (line operations on structured grid)
|  | Line Repulsion | NA (line operations on structured grid)
|  | Line Smooth | NA (line operations on structured grid)
|  | Line Mirrow | NA (line operations on structured grid)
|  | Block Orthogonalize | You can select an orthogonalization zone with a polygon
|  | Block Smooth | You can select a smoothing zone with a polygon
|  | Block Delete Interior | You can select a deletion area with a polygon
|  | Block Delete Exterior | You can select a deletion area with a polygon
|  | Refine grid Locally | Refine is available, but is not the same
|  | Derefine Grid Locally | NA
Irregular Grid
|  | Insert Node | A
|  | Move Node | A
|  | Delete Node | A
|  | Delete node | A
|  | Merge nodes | A
|  | Delete Nodes | A
|  | Delete Edge | A
|  | Split Row or Column | NA (Should this be in regular grid panel?)
|  | Collapse Cell | A (you can achive the same by deleting face (cell) vertices)
|  | Snap to Land boundary | A
|  | Directional casulli Refinement | NA (Should this be in regular grid panel?)
|  | Casulli derefinement | NA (Should this be in regular grid panel?)
| Land boundaries |  | A
| Samples |  | A, only importing, not editing
| Splines |  | A
| Polygons |  | A
| DD Boundaries |  | NA (Delft3D multidomain model)
Operations
| Domain |  | A
| Create |  | A (polygons and splines should be imported separately)
| Delete |  | A
| Convert grid |  | A (Not needed)
| Change Splines into Grid |  | Not sure
| Grow Grid from Boundaries |  | Not sure
| Grow Grid From Splines |  | A
| Grow grid from Polygons |  | A
| Create Rectangular or Circular Grid |  | A
| Regular grid Coarseness |  | Not sure
| Undo grid Operation |  | A
| Orthogonalize grid |  | A
| Flip Edges |  | NA
Grid
|  | Set Line Type to 1D | NA (Grid editor is only 2D)
|  | Set Line Type to 2D | Not sure
|  | Merge Circumcenters | NA
|  | Merge Nodes | A
|  | Merge Grids | NA (What is it?)
|  | Paste Two Grids | NA (What is it?)
|  | Rotate grid administration | NA (What is it?)
Samples
|  | Sample Ridge | NA (What is it?)
| Attach Grids at DD Boundaries |  | NA (Delft3D multidomain model)
| Compile DD Boundaries |  | NA (Delft3D multidomain model)
Coordinate System
| Cartesian Coordinates |  | A
| Spherical Coordinates |  | A
| Translation and Rotation of Cartesian Coordinates |  | NA
| From Cartesian into Spherical Coordinates |  | NA
| From Spherical into Cartesian Coordinates |  | NA