## begroting
Internal budget |  |  |  | Role | Project leader | Application
Gridgeom in C++ - phase 1 (mesh administration and orthogonalization) |  |  |  | Name | Carniato, L. | Pijl, S.P. van der
|  |  |  | Tariff | D | D
|  |  |  | SO-tariff | 132 | 167
Planning | Activity | Product | Hours | Cost
2019-09-01 | Complete basic mesh adminstration in C++ (circumcenters) | updated code | 4 | 528 | 4
2019-09-01 | Writing unit tests for basic node administration | updated code | 8 | 1056 | 8
sep-oct 2019 | Writing orthogonalization in c++ | updated code | 74 | 9908 | 70 | 4
sep-oct 2019 | Testing orthogonalization with different options and meshes | updated code | 50 | 6670 | 48 | 2
sep-oct 2019 | Writing unit tests for orthogonalization | updated code | 8 | 1056 | 8
sep-oct 2019 | Produce a presentation | Presentation | 4 | 528 | 4
|  | Total (hours) | 148 |  | 142 | 6
|  | Total (€) |  | 19746 | 18744 | 1002