## begroting
Internal budget |  |  |  | Role | Project leader | Team member (code reviews)
Gridgeom in C++ - phase 2 |  |  |  | Name | Carniato, L. | Willcox, S.T.
|  |  |  | Tariff | D | A
|  |  |  | SO-tariff | 135 | 100
Planning | Activity | Product | Hours | Cost
Part 1 | Complete orthogonalization with snap to land boundary options | unit tests + hook it up in the grid editor | 26 | 3440 | 24 | 2
Part 1 | Implemente snap to land boundary call | unit tests + hook it up in the grid editor | 10 | 1280 | 8 | 2
Part 2 | Implement splines equations + grid to net converter | unit tests + hook it up in the grid editor | 10 | 1280 | 8 | 2
Part 2 | Implement curvilinear mesh from splines (orthogonal, interactive) | unit tests + hook it up in the grid editor | 34 | 4520 | 32 | 2
Part 2 | Implement curvilinear mesh from splines (transfinite, interactive) | unit tests + hook it up in the grid editor | 26 | 3440 | 24 | 2
Part 3 | Add third party triangulation library |  | 26 | 3440 | 24 | 2
Part 3 | Implement triangular mesh in polygon | unit tests + hook it up in the grid editor | 10 | 1280 | 8 | 2
Part 4 | Refine polygon perimeters | unit tests + hook it up in the grid editor | 18 | 2360 | 16 | 2
Part 4 | Mesh boundary to polygon | unit tests + hook it up in the grid editor | 26 | 3440 | 24 | 2
|  | Total (hours) | 186 |  | 168 | 18
|  | Total (€) |  | 24480 | 22680 | 1800

## api calls
| API calls | FORTRAN subroutines
1 | ggeo_snap_to_land_boundaries_dll | find_nearest_meshline, make_path, masknodes, maskcells, shortest_path, get_kstartend, get_kstartend2, dmeshwidth
2 | ggeo_unstructured_mesh_to_curvilinear_mesh_dll | gridtonet
3 | ggeo_curvilinear_mesh_from_splines_ortho_dll | spline2curvi, get_splineprops, make_wholegridline, addSplinePoint, get_splineprops, comp_edgevel, growlayer, postgrid, spline2poly, merge_spline2curvigrids, comp_gridheights
4 | ggeo_curvilinear_mesh_from_splines_dll | curvilinearGridFromSplines,SPLRGFR
5 | ggeo_mesh_from_polygon_dll | createsamplesinpolygon, Triangulatesamplestonetwork, gridtonet, delpol, check triangle
6 | ggeo_refine_polygon_dll | refinepolygonpart, accumulateDistance, averageDiff, mapToPolyline, interpOnPolyline,SMODPLA
add spline class
add sample class
add triangulation class